## Sheet1
Test ID | Functionality | Scenario | Expected Result | Actual Result | Comments | Failure Snapshot
1 | Sign Up | Giving the basic info. The beta info has to be sent to the admin. | Email will be sent to the admin for enabiling workspace | Works as expected
2 | Sign In | Verifying the Login credentials. | Access is granted. Redirects to To-Do list. | Works as expected
3 | To-Do list | Tasks can be assigned. Mandatory fields are checked. Pop up's open. | Assign's the task to the selected internal user. | Works as expected
4 |  | Priorities can be changed. | Updates the information. | Works as expected
5 |  | Status can be changed. | Updates the Status | Works as expected
DashBoard
6 | Active Jobs | Active jobs are updated properly. | When ever the job is added it adds the active jobs. | Works as expected
7 | Interviews Scheduled | Interview scheduled as per the calender | Updating the interview in athe dashboard. As per the calendar. | Works as expected
8 | Position yet to close | Calculates the total job requirments and displays. | Position yet to close should calculate the Jobs-remaining count |  | The count of position yet to is not calculated as per the Jobs-remaining.
9 | Target Achievement | The montly report of the specified Recruiter | By selecting a recruiter and the specified month the report should be displayed | Works as expected
10 | Target Achievement - Clients | Should be able to download the report | Should be able to download the report in SVG , PNG , CSV format's. | Works as expected
11 | Calendar | View in months , weeks , day , agenda | The output should be changing accordingly | Works as expected
12 |  | Interviews can be sheduled | Interviews should be notified
13 |  | Schedule a New interview | Add the newly Scheduled interview to the calendar |  | The date can be set by the drop down . The time can also be scheduled by a drop down box .
JOB
14 | Search Jobs | Should display the Jobs according to the alphabets typed |  | Works as expected
15 | Add jobs | back and submit button differs from other button in other pages
16 |  | Toggle for internal job | When toggled it should be marked as a internal job | Works as expected
17 |  | Add job | Add's the job to the specified client | Works as expected
18 |  | Mandatory field | Mandatory fields should be filled to submit | Works as expected
19 | Client | Drop down the Client's list | List of client's | Works as expected
20 | Primary Recruiter | Drop down of the recruiter | List of recruiter's for the specified client if Client is selected | Works as expected
21 | Industry Sector's | Drop's down the list of sector's | List of Industry sector's | Works as expected
22 | Primary skills required | Pop's down a drop down for specified sector | Drop down box appears for the selected sector | Works as expected
23 | Job title | Pop's down a drop down for specified sector | Drop down box appears for the selected sector | Works as expected
24 | Filters - Client | Search bar |  | Works as expected
25 | Filters - Severity | Select the Severity to filter | Filters according to the selected severity | Works as expected
26 | Filters - Primary Recruiter | Search bar |  | Works as expected | Empty data is stored
27 | Filters - Secondary Recruiter | Search bar |  | Works as expected | Empty data is stored
28 | Sort -by | Sort the data accordinly | Sort the data as per the specified option | Works as expected
29 | Job - profile | Shedule interview , Reject , Archieve |  | Works as expected
30 |  | Click profile to select the status | Update the profile to Specified table |  | If the profile is selected and updated to rejected there is no updation happening
31 |  | Delete , add new candidate |  | Works as expected
Candidate
32 | Verified | Search bar | Search the required candidate | Works as expected
33 |  | Genarate form link | Should generate a form link that has to be sent to the candidate | Works as expected
34 |  | Add candidates |  | Works as expected
35 |  | Actions | Shares resume via mail | Works as expected
36 |  | Filters should display the specified data according the selected inputs | Send form to Candidate | Works as expected | The primary and secondary skills have name of the candidates . Location is not in the alphabetical order in the drop down list.
37 | Not Verified | Search bar | Search bar filter | Works as expected
|  | Years of exp |  |  | The years of experience cannot be in a decimal .
38 |  | Show column's button | Filter's and display's the selected column's | Works as expected
39 |  | Genarate form link | Should generate a form link that has to be sent to the candidate | Works as expected
40 |  | Actions | Shares resume via mail | Works as expected
41 |  |  | Verify and add's the candidate to verified section | Works as expected
42 |  |  | Archive a candidate | Works as expected
43 | Resume Processor | Upload resume | Parses the required data into Not verfied column |  | Data is incorrectly parsed
Manage
44 | Add User - Internal | Search bar | Search the required user | Works as expected
45 |  | Toggle to view archived user | Display the archived user | Works as expected
46 |  | Add user | Add user using mandatory field's | Works as expected
47 | Add User - Client | Search bar | Search the required Client | Works as expected
48 |  | Toggle to view archived user | Display the archived user | Works as expected
49 |  | Add user | Add user using mandatory field's | Works as expected
50 | Add User - Hiring partner | Search bar | Search the required Hiring partner | Works as expected
51 |  | Toggle to view archived user | Display the archived user | Works as expected
52 |  | Add user | Add user using mandatory field's | Works as expected
53 | Client | Search bar | Search the required client | Works as expected
54 |  | Add or remove column | Selected Row and Column to be displayed in the table | Works as expected
55 |  | Add clients | Clients can be added with the mandaory field's | Works as expected
56 |  | Add clients - Bill to | Data retrieveing from the mandatory fields | Works as expected
57 |  | Actions | Delete a Client | Works as expected
Hiring partner
Reports
58 | Recruiter efficiency metrics
59 | Target Achievement | Export | Report can be downloaded as CSV and PDF | Works as expected
60 | Quality of Resumes | Export | reports can be dounloaded in CSV and PDF | Works as expected
61 | Candidate Progess | Job Title | Filters the required job title | Works as expected
|  | Job stage | Filters the required job
|  | Export | reports can be dounloaded in CSV | Works as expected
| Not Verified | Displays the data got from the resume processor | First Name , Last Name , Contact , email , skills should be displayed |  | The user details can be displayed .
| Resume Processor | Data should be parsed from the resume uploaded and adds the data to not verified | First Name , Last Name , Contact , email , skills should be parsed form the resumes |  | The data is incorrrectly retrieving
Manage
| Add user , Client , Hiring Partner |  |  | Works as expected
Reports
| Target Achievement Report |  |  |  | The user can be specified
Configure
| Dash Board |  |  |  | The Titles should be in plural form .
| ATS | Industry sector , Skills , JD Template |  |  | Skills are limited .
| Onboarding | Designation , Employment Type , Documentations |  | Works as expected
Profile
| Change Pswd | Enter the old pswd. New pswd to be entered. Re-entering new pswd. | Email will be sent to the user. | Pswd Updating
| Take your | Should navigate the new user . |  |  | It only navigates in a single page .
| Home | Should redirect to the To-Do list |  | Works as expected